## Slide 1: Managing team Meeting Jean-Marc THIRIET Université Joseph Fourier Grenoble
Heraklion (Greece),
30th November – 1st December 2007
Ευχαριστώ, Γιώργος !

## Slide 2: Apologies for absences
C. Burkley (IE)
H. Fremont (FR)
Z. Mrozek (PL)

## Slide 3: Agenda (1/2)
FRIDAY 30th November 2007
- 9.00 Welcoming session A. GENERAL SESSION ON THE PROJECT (JM Thiriet) - 9.15 General information on the project, feedback from the progress report - 9.30 New website - 9.45 Leaflet, strategy of dissemination - 10.15 Break - 10.30 General management of the money - 12.00 LUNCH - 13.30 B. PARALLEL SESSIONS (each task + dissemination + contacts with industry + monitoring group + BEST) - 16.00 Break COMMON SESSION: FEEDBACKS - 16.30 TASK 1.1 : TUNING (Feedbacks from the questionnaires (students, academics, employers, graduate), preparation of the final outcome (analysis/synthesis of the questionnaires, format of the final outcome, dissemination strategy, organisation of the work)) (T. Ward, J. Jasenek) - 17.30 TASK 1.3 : Accreditation (Feedbacks from the questionnaires, preparation of the final outcome (analysis/synthesis of the questionnaires, format of the final outcome, dissemination strategy, organisation of the work)) (D. Pasquet, C. Burkley, F. Maciel-Barbosa)

## Slide 4: Agenda (2/2)
SATURDAY 1st December 2007
- 9.00 TASK 2 : Quality (Feedbacks from the surveys, preparation of the final outcome (analysis/synthesis of the surveys, format of the final outcome, dissemination strategy, organisation of the work)) (J.L. Marzo-Lazaro, D. Deniz) - 10.00 TASK 3.1 : Bologna-Process Observatory (Feedbacks from the surveys, preparation of the final outcome (analysis/synthesis of the surveys, format of the final outcome, dissemination strategy, organisation of the work)) (MJ Martins, JM Thiriet) - 10.30 Break - 10.45 TASK 3.3: Mobility (Feedbacks from the questionnaires, preparation of the final outcome (analysis/synthesis of the questionnaires, format of the final outcome, dissemination strategy, organisation of the work)) (H. Yahoui) - 11.30 Contacts with industry: Z. Mrozek (Excused) - 12.00 LUNCH - 13.30 Dissemination action: J. Barsics - 14.15 Partnership with BEST, organisation of a BaCo - 15.00 Organisation of the external monitoring: J.C. Burguillo - 15.45 Pause - 16.15 General Discussion and Synthesis: (Final synthesis, global organisation of the work for the last year) (JM Thiriet) - 17.00 Feedback from the monitoring group (J.C. Burguillo & al.) - 17.30 End of the meeting

## Slide 5: Beyond the agenda
EAEEIE (Jan Ligus)
EAEEIE’08 Tallinn (Gert Jervan)
New TN project (Cristian Perra, Hamed Yahoui, Jan Ligus, Maria Joao Martins, Michael Hoffmann), meeting in Lisboa 13th October 2007

## Slide 6: General information on the project
February 2008, General meeting for coordinators
Deadline for new projects: 29th February 2008
  2-day information in the Commission: 18 and 21 January 2008

## Slide 7: General information on the project: Next meetings
Working group meeting | Grenoble (France) | 13 March => EAEEIE PC meeting and GA Council 14-15 March 2008
Joint event assessment with BEST | To be defined | To be defined, 3rd year
3rd general meeting | EAEEIE conf 2008, Tallinn (Estonia), | Sunday 29th June 2008 ??
Last meeting, preparation of the Final Report | ??? | End August or September 2008 (end of eligibility period)

## Slide 8: Feedback from the progress report

## Slide 9: General management of the money

## Slide 10
General management of the money Financial aspects (practical)
Type of costs | Approved budget (€uro) | Community grant (€uro) | Percentage of funding
1. Staff costs | 607 015 |  | 
2. Direct costs |  |  | 
2.a. Travel and subsistence | 438 000 |  | 
2.b Equipment and materials | 5 500 |  | 
2.c Sub-contracting, consultancy and other external services | 78 945 |  | 
2.d Other | 33 756 |  | 
Total for direct costs | 556 201 |  | 
3. General costs | 87 553 |  | 
TOTAL | 1 250 769 | 400 480 | 32,02

## Slide 11: General management of the money Travel and subsistence costs
Calculation of subsistence costs: 1 per diem / night + ½ per diem for travel (NOT MORE)
Susbsistence costs eligible for external experts coming from outside Socrates countries (but not Travel costs)
Travel and subsistence costs for students participating to the plenary meeting are eligible

## Slide 12: General management of the money Co-financing for Travel and subsistence » and « other costs »
Declaration of costs (travel, accomodation) as co-financing of your institution for « travel and subsistence »
  Other travel and subsistence (for instance days for your participation to the EAEEIE conference)
Declaration of costs (registration) as co-financing of your institution for « other costs »
  Ex: registration for the EAEEIE conference
TAKE CARE ! Only in the eligible zone (EU27 + NO + IS + FL + TR)

## Slide 13: General management of the money Staff costs – key points
The staff costs related to all persons involved in the project by institution can be charged into the project, according to the time effectively spent => BE REALISTIC !
The costs should be calculated on the hourly, daily, monthly gross cost (salaire brut) multiplied by the number of hours, days or months worked
The beneficiary and partners must keep full and accurate records
Personnel costs should not exceed the norm for the labour market concerned
Volonteer costs (bénévoles) not eligible – real costs only

## Slide 14: General management of the money Equipment
Hardware and equipments, when > 1000 €uro are submitted to depreciation (33.33 % per annum)
Adjusted to the percentage of use in the project
Pieces of equipment purchased before the project period are not eligible
Be aware of internal rules of depreciation, if different from the Commission’s rules
BILL OF A COMPUTER > 1000 € (around the beginning of the project)
Pour récupérer de l’equipement, il faut que les collègues apportent une facture d’ordino dans la période éligible (début du projet) => on mettra de l’amortissement

## Slide 15: General management of the money Transfer of money to the partners
Points gotten from some activities
  Coordination (3 points per year)
  Managing team, monitoring group, tasks managers (2 points per year)
  Organisation of meetings (2 points per meeting)
  Participation to a meeting (Lyon, Santander, Craiova, Wels, Bratislava, Prague, Heraklion, Grenoble, Tallinn) (1 point per participation)
  Participation to specific events representing EIE-Surveyor (Brussels, Bucharest, Lviv, SEFI, TN forums) (1 point per participation)
  Declaration of staff costs (0,5 point per year)
  Declaration of co-financing (travel and subsistence)

## Slide 16: General management of the money Transfer of money to the partners
  Declaration of co-financing (other costs)
  Declaration of co-financing (equipment)
  Déclaration publications + impact of the TN + dissemination actions (0,2 point par action)
  Préparations questionnaires Tuning
  Tests questionnaires Tuning+Hamed
  Remplissage questionnaires Tuning+Hamed
  Participation task1.3 Accreditation
  Acteurs task Quality
  Préparation Questionnaires Hamed
  Participation task 3.1 monograph

## Slide 17: General management of the money Transfer of money to the partners
Main rule
  Written agreement signed
  Data update on the web-site
Inputs
  Number of hours declared and justified
  Finantial declaration from the institutions (~30 % can be granted), declared en justified

## Slide 18: General management of the money Transfer of money to the partners
Eligible costs
  Declared Staff costs (3 years)
    Declaration by the institutions
  + Travel and subsistence (3 years)
    Declaration by the institutions
    Automatic co-financing (difference between the authorized per-diem and the actual per-diem)
  + Other costs (3 years)
    Declaration by the institutions (registration to conferences, other declarations)
    Declaration by the institutions (administrative costs)
  + Equipment (damping / amortissement)
Amount of money (~30 % of the eligible costs) – the amount already transfered (generally reimbursement of travel and subsistence for the past meetings)

## Slide 19: General management of the money Administrative contact in Nancy
Marie-Lise Lemarquis
ESSTIN
2, rue Jean Lamour
54 519 Vandoeuvre les Nancy cedex
FRANCE
Fax: +33 3 83 68.50.01
Marie-Lise.Lemarquis@esstin.uhp-nancy.fr

## Slide 20: Balance on the tasks of the project

## Slide 21: For each task
Stage of the task
What remains to be done ?
Action plan for the last year
Dissemination action for the outcome (final product/result) of the task