## Slide 1: 3rd General Meeting Meeting Jean-Marc THIRIET Université Joseph Fourier Grenoble
Tallinn (Eesti),
29th June 2008
Thank you, Gert !

## Slide 2: Apologies for absences
J. Barsics (BE, Liège)
L. Lhotska (CZ, Prague)
C. Perra (IT, Cagliari)
M.J. Martins (PT, Lisboa)
M. Robert (FR, Nancy)
M. Diprose (Spectrum Ltd, UK)

## Slide 3: Agenda
Sunday 29th June 2008
- 9.00 EIE-Surveyor plenary session
  General information – Final report (JM Thiriet)
  Financial aspects (JM Thiriet)
Outcomes of the project
* Data from the questionnaires (J. Ligus) * TASK 1 Tuning (A. Ward & J. Jasenek) * TASK 1.3 Accreditation (D. Pasquet, C. Burkley & F. Maciel-Barbosa) * TASK 2 Quality (D. Deniz, JL Marzo-Lazaro & D. Genon-Catalot) * TASK 3 Bologna Observatory (JM Thiriet & G. Jervan) * TASK 3.3 Portal (H. Yahoui) * Feedback from the monitoring group with external monitors

## Slide 4: General Information
New LLP thematic network
ELLEIEC
Enhancing Lifelong Learning for the Electrical and Information Engineering Community
Hamed Yahoui (Université Claude Bernard Lyon 1 coordinator)
2008-2011

## Slide 5: Final report

## Slide 6: Balance of the consortium (October 2005, beginning)
111 partners
3 European societies
AT 2
BE 5
BG 4
CY 1
CZ 3 + 1 company
DE 5 + 1 company + 1 chapter IEEE
DK 1
EE 1
ES 9
FI 2
FR 21 + 1 society + 1 chapter IEEE
GR 2
HU 2
IE 1
IS 1
IT 5
LT 1
LV 1
MT 1
NL 1
NO 1
PL 5 + 1 company
PT 7
RO 6
SE 2
SI 2
SK 2
TR 4
UK 2
2 associated (UA and LB)

## Slide 7: Balance of the consortium (January 2007, progress report)
111 partners – 7
3 European societies
AT 2
BE 4
BG 2
CY 1
CZ 3 + 1 company
DE 5 + 1 company + 1 chapter IEEE
DK 0
EE 1
ES 8
FI 2
FR 21 + 1 society + 1 chapter IEEE
GR 1
HU 2
IE 1
IS 1
IT 5
LT 1
LV 1
MT 1
NL 1
NO 1
PL 5 + 1 company
PT 7
RO 6
SE 2
SI 1
SK 2
TR 4
UK 2
2 associated (UA and LB)

## Slide 8: Balance of the consortium (January 2007, progress report)
111 partners – 7 + 6 = 110
4 European societies
AT 2
BE 4
BG 2
CY 1
CZ 3 + 1 company
DE 5 + 1 company + 1 chapter IEEE
DK 0
EE 1
ES 8
FI 2
FR 23 + 1 society + 1 chapter IEEE
GR 2
HU 2
IE 1
IS 1
IT 5
LT 1
LV 1
MT 1
NL 1
NO 1
PL 5 + 1 company
PT 7
RO 7
SE 2
SI 1
SK 2
TR 4
UK 2 + 1 company
2 associated (UA and LB)

## Slide 9: Balance of the consortium (between progress and final report)
110 partners
4 European societies
AT 2
BE 4
BG 2
CY 1
CZ 3 + 1 company
DE 5 + 1 company + 1 chapter IEEE
DK 0
EE 1
ES 8
FI 2
FR 23 + 1 society + 1 chapter IEEE
GR 2
HU 2
IE 1
IS 1
IT 5
LT 1
LV 1
MT 1
NL 1
NO 1
PL 5 + 1 company
PT 7
RO 7
SE 2
SI 1
SK 2
TR 4
UK 2 + 1 company
2 associated (UA and LB)

## Slide 10: Balance of the consortium (September 2008, final report)
110 partners – 8 = 102
4 European societies
AT 2
BE 4
BG 2
CY 1
CZ 3 + 1 company
DE 4 + 0 company + 1 chapter IEEE
DK 0
EE 1
ES 8
FI 2
FR 23 + 1 society + 1 chapter IEEE
GR 2
HU 2
IE 1
IS 1
IT 5
LT 1
LV 1
MT 1
NL 0
NO 1
PL 5 + 0 company
PT 6
RO 7
SE 0
SI 1
SK 2
TR 3
UK 2 + 1 company
2 associated (UA and LB)

## Slide 11: Information from partners 15th August
Impact of the TN, unexpected outcome
Bibliographical references of members (Dissemination)
Dissemination actions of partners

## Slide 12: General management of the money

## Slide 13
General management of the money Financial aspects
Type of costs | Approved budget (€uro) | Community grant (€uro) | Percentage of funding
1. Staff costs | 607 015 |  | 
2. Direct costs |  |  | 
2.a. Travel and subsistence | 438 000 |  | 
2.b Equipment and materials | 5 500 |  | 
2.c Sub-contracting, consultancy and other external services | 78 945 |  | 
2.d Other | 33 756 |  | 
Total for direct costs | 556 201 |  | 
3. General costs | 87 553 |  | 
TOTAL | 1 250 769 | 400 480 | 32,02

## Slide 14
General management of the money Actual budget (June 2008)
Type of costs | Approved budget (€uro) | Present budget (€uro) | Percentage of approved budget
1. Staff costs | 607 015 | 600051,79 | 98,8
2. Direct costs |  |  | 
2.a. Travel and subsistence | 438 000 | 222833,53 | 50,87
2.b Equipment and materials | 5 500 | 1140,60 | 20,73
2.c Sub-contracting, consultancy and other external services | 78 945 | 22611,07 | 28,64
2.d Other | 33 756 | 20312,08 | 60,17
Total for direct costs | 556 201 | 266897,28 | 47,98
3. General costs | 87 553 | 65254,23 | 74,53
TOTAL | 1 250 769 | 932203,31 | 74,53

## Slide 15
General management of the money Expected budget (end of the project)
Type of costs | Approved budget (€uro) | Present budget (€uro) | Percentage of approved budget
1. Staff costs | 607 015 | 667716 | 110 %
2. Direct costs |  |  | 
2.a. Travel and subsistence | 438 000 | 300000 | 68,5 %
2.b Equipment and materials | 5 500 | 3000 | 54%
2.c Sub-contracting, consultancy and other external services | 78 945 | 25000 | 31,66 %
2.d Other | 33 756 | 30000 | 88,9 %
Total for direct costs | 556 201 | 358 000 | 64,36 %
3. General costs | 87 553 | 77 204 | 88,17 %
TOTAL | 1 250 769 Grant 400 480 | 1 102 920 | 88,17 % Grant 353 155

## Slide 16: General management of the money Travel and subsistence costs
Calculation of subsistence costs: 1 per diem / night + ½ per diem for travel (NOT MORE)
Subsistence costs eligible for external experts coming from outside Socrates countries (but not Travel costs)
Travel and subsistence costs for students participating to the plenary meeting are eligible
Declaration of costs (travel, accomodation) as co-financing of your institution for « travel and subsistence »
  Other travel and subsistence (for instance days for your participation to the EAEEIE conference)

## Slide 17: General management of the money Staff costs – key points
The staff costs related to all persons involved in the project by institution can be charged into the project, according to the time effectively spent => BE REALISTIC !
The costs should be calculated on the hourly, daily, monthly gross cost (salaire brut) multiplied by the number of hours, days or months worked
The beneficiary and partners must keep full and accurate records
Personnel costs should not exceed the norm for the labour market concerned
Volonteer costs (bénévoles) not eligible – real costs only

## Slide 18: Equipment and material
total value < € 1 000, the full purchase value is eligible, adjusted to the percentage use in the project;
purchase price > € 1 000, hardware and equipment are considered as having a life expectancy of three years.
  Example: the allowable cost in year one for a piece of equipment worth € 10 000, which is used 50 % for the project, amounts to € 1 666
10 000 x 33.33% x 50% = € 1 666.
Documents required: invoices

## Slide 19: Other costs
Bank charges :
  opening or maintaining of an account established especially for the project,
  bank transfer and exchange costs relating to receipts and payments for eligible expenditure under the project
  => contacter le service financier pour récupérer les coûts bancaires des transferts
Costs incurred in producing, translating and publishing documents, performed by one of the member organisations
Internet communication costs in duly justified cases for projects where activities require very intensive use of this type of communication
Hiring of conference halls or training premises
Documents required: Invoices
Declaration of costs (registration) as co-financing of your institution for « other costs »
  Ex: registration for the EAEEIE conference
  EAEEIE membership fees
  Renting of rooms
TAKE CARE ! Only in the eligible zone (EU27 + NO + IS + FL + TR)
Add justifications
Keep records of all your documents…
(The European Commission can request documents from you !)

## Slide 20: General costs
communication costs (postage, fax, telephone, mailing, etc.)
infrastructure costs (rent, electricity, etc.) of the premises where the project is being carried out, in proportion to the use of these premises by the project
office supplies
photocopies.
The beneficiary will not be required to produce supporting documents for general costs

## Slide 21: Transfer of money to the partners

## Slide 22
Points Transfer of money to the partners
Coordination | 4 for Nancy, 2 for Grenoble
Managing team, monitoring group, tasks managers | 2 points per year
Organisation of meetings | 2 points per meeting
Participation to a meeting | 1 point per participation
Tuning | 
Accreditation | 
Quality | 
Bologna | 
Mobility | 
Other actions | 0,2 point per line in the tables

## Slide 23: General management of the money TASK 1.1 TUNING
Development of Questionnaire – 4 points
Test and Correct the Questionnaire – 1 point
Contribution to meetings ???
  Grid of meeting and engagement of partner
Based on number of questionnaires submitted
  Grid of number of responses of partner
Statistical studies
Redaction and publication of the outcomes

## Slide 24: General management of the money TASK 1.3 Accreditation
Coordination task 1.3 Accreditation
Participation task 1.3 Accreditation
Redaction and publication of the outcomes

## Slide 25: General management of the money TASK 2 Quality
Who did what during the life time of the project ?
  SCORM ---
  Modified SCORM ---
  Questionnaire ---
  PILOTS 1-4 and Real Server ---
  Contact Management ---
  Attribution of points to all who have joined the meetings for task 2 and contributed
  Attribution of points to those who have done the testing
  Attribution of points to partner coordinators who will put real data into the e-Cat.
Redaction and publication of the outcome

## Slide 26: General management of the money TASK 3.1 Observatory
Management of the task
Authors of general papers – 2 points
National contact (update of the data for a country) – 0,2 point per page
Redaction and publication of the outcome

## Slide 27: General management of the money TASK 3.3 Mobility
Strategy at the beginning of the task and, main questions to ask in the questionnaires
Strategy of the task and main question to ask in the questionnaires
Design of the complete Questionnaires
Correction of the questionnaires phase 1 - Student Questionnaire only
Correction of the questionnaires phase 2 - Surveyor questionnaire and mobility questionnaire
Correction of the questionnaires phase 3
Testing of the questionnaires
Strategy for the end of the task and main questions to ask in the questionnaires
Extraction of result from questionnaires
Report on questionnaires
Finalising Report on questionnaires
Design of the Web portal
Experiment of the Web portal
Report on the web portal

## Slide 28: Example
Declared budget | Maximum grant (30 % of the budget) | Possible grant (number of points * value of 1 point) | Effective grant | Part of the grant used (reimbursement of previous travels) | Part of the grant to transfer
322 | 322*0,3= 96,6 | 900 | 96,6 | 0 | 96,6 -0= 96,6
28471,24 | 28471,24*0,3= 9541,37 | 7830 | 7830 | 2125,24 | 7830-2125,24= 5704,76

## Slide 29: General management of the money Administrative contact in Nancy
Marie-Lise Lemarquis
ESSTIN
2, rue Jean Lamour
54 519 Vandoeuvre les Nancy cedex
FRANCE
Fax: +33 3 83 68.50.01
Marie-Lise.Lemarquis@esstin.uhp-nancy.fr

## Slide 30: Advancement state of the tasks

## Slide 31
« Points » and list of partners involved in the task
Website (pages outcomes)
Prototype of the result
Dissemination action for the outcome (list of addresses for the dissemination)
  National level
  European level

## Slide 32: Tasks
T1.1 Competences, TUNING (A. Ward, J. Jasenek)
    General competences
    Specific competences
T1.3. Methodology for accreditation
  (D. Pasquet, F. Maciel-Barbosa, C. Burkley, M. Hoffmann)
T2. Internet as educational resource for EIE education
(J.L. Marzo-Lazaro, D. Deniz, D. Genon-Catalot)
T3. Survey, BMD-process in Europe (M.J. Martins, G. Jervan)
  T3.1. Bologna process in EIE at the bachelor, master and PhD levels
  T3.3 Portal on mobility, EIE curricula (H. Yahoui)

## Slide 33: Tasks
TRANSVERSAL TASK: Portal for the various tasks (J. Ligus)
The monitoring group : Responsible: Hélène Frémont Composition: Juan Carlos Burguillo, Karl Guðmundsson
External monitoring
  Jacques Citerne
  Yves Danto
GENERAL DISSEMINATION POLICY (J. Barsics)

## Slide 34
Maximum per diem
Country | Maximum in € | Country | Maximum in €
BE Belgium | 150 | IS Iceland | 183
DK Denmark | 179 | LI Liechtenstein | 174
DE Germany | 127 | NO Norway | 171
GR Greece | 113 | BG Bulgaria | 157
ES Spain | 141 | CZ Czech Rep. | 214
FR France | 130 | EE Estonia | 129
IE Ireland | 165 | CY Cyprus | 100
IT Italy | 130 | LV Latvia | 174
LU Luxembourg | 143 | LT Lithuania | 126
NL Netherlands | 148 | HU Hungary | 136
AT Austria | 122 | Malta | 86
PT Portugal | 143 | PL Poland | 227
FI Finland | 156 | Romania | 185
SE Sweden | 157 | SI Slovenia | 148
UK United Kingdom | 199 | SK Slovakia | 164
 |  | TR Turkey | 138