## Slide 1
Monitoring and Evaluation issues
Tallinn 29th June 2008
EIE-Surveyor
Hélène FREMONT, Bordeaux1 University (FR)
Karl Gudmundsson, University of Iceland (IS)

## Slide 2
Recommendations from the Monitoring Group (Grenoble March 2008)
Pragmatic Strategy for the next last months
Send specific e-mails to partners in order to get answers
Task’s managers must be even more active
Solve the safety problems of the questionnaire website
Update the website (monitoring group/dissemination task)
    Everything seems to have correctly evolved
Monitors and managers should organise the external monitoring

## Slide 3
External monitoring organisation
Proposition of tasks
Global evaluation of the organisation / life of the whole project
Time evolution of the project
Evaluation task by task : initial purposes / final outcomes
Two emeritus professors accepted
Jacques CITERNE : Prof. at Rennes University (Electronics and telecommunications)
  Outcomes evaluation
Yves DANTO : Prof. at Bordeaux University (Reliability of microelectronics components)
Project’s organisation evaluation

## Slide 4
Monitoring Group Work Tallinn, June 2008
Facilities were very good
Thank You, Gert